## Лист1
ID | Work Packages | Performers | Labor intensity (Hours / Day) | Duration (Days) | Cost of key factors (Units /Hour) | Required resources | Cost estimates
Marketing Research
1.1.1. | Creating & translating surveys | Marketer team | 6 | 2 | 8 | Computer, Internet | 96
1.1.2. | Uploading surveys to Google Forms & sharing it in different social networks (VK, Reddit, Facebook, LinkedIn) |  | 6 | 1 | 8 |  | 48
1.1.3. | Gathering information & statistics and creating a profile of a future customer | Business Analyst | 4 | 4 | 4 |  | 64
Specification Development
1.2.1 | Creating specifications for mobile application OS (version, camera and etc.) | Business Analyst | 6 | 2 | 8 | Computer, Internet | 96
Visual & Technical Design
Technical design
2.1.1 | Designing user cases of using application | Business Analyst, Developer Team | 4 | 3 | 12 | Computer | 144
2.1.2 | Creating list of interactable social networks and carefully reading license agreements of those social networks (there may be a lot of problems with licensing) |  | 4 | 3 | 8 |  | 96
2.1.3 | Listing all necessary types of information gathered from social networks |  | 1 | 1 | 12 |  | 12
Visual design
2.2.1 | Designing customer visit card default template | Designer | 8 | 1 | 6 | Computer, Design Software, Internet | 48
2.2.2 | Designing informational marker (VuMark) |  | 8 | 1 | 6 |  | 48
Development
Vuforia (AR Engine)
3.1.1. | Registrating account, getting valid license. Providing payment operations (if it's need) | Business Analyst & Developer team | 3 | 1 | 12 | Computer, Internet | 36
3.1.2 | Loading visit card & VuMark templates into Vuforia Target Manger |  | 1 | 1 | 8 |  | 8
API
3.2.1. | Setting up basic server infrastructure, ordering server cloud-base space | Developer team | 8 | 1 | 8 | Computers, Internet | 64
3.2.2. | Creating basic models, DTO models (data transfer objects) of entities that are used in application working flow | Business Analyst & Developer team | 8 | 4 | 12 | Computers, Internet, Development Software | 384
3.2.3 | Basic development: installing additional software, creating projects (source containers) | Developer team | 8 | 1 | 8 |  | 64
3.2.4 | Writing basic server side code: request handlers, users registration, authentication & authorization, media controllers |  | 8 | 2 | 16 |  | 256
3.2.5 | Creating developer accounts and applications in social networks from the list |  | 4 | 2 | 16 |  | 128
3.2.6 | Writing functionality that will interact with social networks from the list |  | 8 | 4 | 16 |  | 512
3.2.7 | Writing functionality that will allow to automaticly update social information about customers |  | 8 | 3 | 16 |  | 384
3.2.8 | Writing functionality that will allow to manually update customer settings and additional information |  | 8 | 2 | 16 |  | 256
3.2.9 | Adding functionality to gather information about social accounts of a customer trough API Request |  | 8 | 2 | 16 |  | 256
3.2.10 | Writing additional code for server, data protection. Cleaning code |  | 6 | 3 | 12 |  | 216
3.2.11 | Creating documentation of the API |  | 8 | 2 | 24 |  | 384
Mobile Application
3.3.1 | Programming basic recognition of visit cards and VuMarks | Developer team | 8 | 4 | 16 | Computers, Internet, Development Software | 512
3.3.2 | Development of client-server communication |  | 8 | 3 | 16 |  | 384
3.3.3 | Designing & creating virtual 3D with necessary content |  | 8 | 6 | 16 |  | 768
3.3.4 | Creating functional for interacting with virtual 3D objects. (Making social networks clickable, rotation of 3D scene, scrolling, zooming and etc.) |  | 8 | 5 | 16 |  | 640
3.3.5 | Creating local storage for storing scanned visit cards to view them later |  | 8 | 2 | 16 |  | 256
3.3.6 | Creating functional for viewing saved visit cards |  | 8 | 3 | 16 |  | 384
3.3.7 | Creating exception handlers |  | 8 | 1 | 16 |  | 128
3.3.8 | Creating functional for importing unknown contacts from recognized visit card to user phone |  | 8 | 1 | 16 |  | 128
3.3.9 | Designing, creating & programming user interface |  | 8 | 1 | 16 |  | 128
Testing
Configuration testing
4.2.1. | Testing of installation of the product | QA engineer | 2 | 1 | 5 | Different mobile phones | 10
4.2.2. | Testing of working with different hardware settings and with different devices |  | 2 | 3 | 8 |  | 48
4.2.3. | Testing of removal of the product from the system |  | 2 | 1 | 5 |  | 10
Documentation
4.5.1. | Test result report | QA engineer | 10 | 2 | 20 | Computers | 400
Release
Deployment of software
5.1.1. | Deployment final release to cloud hosting | Developer Team | 4 | 1 | 8 | Computer, Internet | 32
5.1.2. | Deploy into Google Play and App Store |  | 4 | 2 | 8 |  | 64
Advertising
5.2.1. | Social networks advertising (Instagram, VK, Twitter, LinkedIn, Facebook) | Marketer Team | 8 | 7 | 4 | Computers, Internet | 224
5.2.2. | Contextual advertising |  | 8 | 1 | 7 |  | 56